## RACI
| Chief Finance Officer | EMEA Director of Finance | EMEA Director of Operations (SPL) | VP for Global Operations | VP for Global Sales & Marketing | EMEA Director of Production | EMEA Director of R&D | EMEA Director of Distribution | Chief Information Officer | EMEA Director of IT Systems
Determining scope of initiative | I | R | R | A | C | C | C | C | C | C
Creating the business case | I | I | R | A | C | C | C | C | C | C
Funding approval | I I: R/A; R I: R; R R: I; A A: I
Providing information on impact to Sales workforce | R R: R/A; A A: I; C C: C
Providing information on impact to Marketing workforce | R R: R/A; A A: I; C C: C
Providing information on impact to Production workforce | R R: R/A; A A: I; C C: C
Providing information on impact to R&D workforce | R R: R/A; A A: I; C C: C
Providing information on impact to Distribution workforce | R R: R/A; A A: I; C C: C
Providing information on impact to IT workforce | R R: R/A; A A: I; C C: C; C C: C
Determining overall stakeholder impacts | bar: R R to A A
Creating onboarding plan |  |  | R | A | C | C | C | C | C | C
Approving onboarding plan | I I: R/A; R I: R; R R: I; A A: I
Implementing onboarding plan |  | I | R | A | I | I | I | I | I | I
Creating adoption plan |  |  | R | A | C | C | C | C | C | C
Approving adoption plan | I I: R/A; R I: R; R R: I; A A: I
Implementing adoption plan |  | I | R | A | I | I | I | I | I | I
Measuing and reporting (KPIs and milestones) | R I: I; R R: R; A A: A
Evaluating success and approving further phases | I I: I; R I: R/A; R R: C; A A: C
R = Responsible | I I: The person or people who actually perform the task. This person or group of people is often though not always appointed by the Accountable person.
A = Accountable | I I: The person who is ultimately answerable for ensuring the task is performed to the appropriate standards of quality, time, etc (this should always be just one person)
C = Consulted | I I: These are additional people whose opinions, expertise or other inputs are sought by the Responsible person or people in the process of performing the task
I = Informed | I I: These are people who are not involved in either the performance or oversight of the task, but who need to know when the task has been completed (for example in order to know when to start another task which they are responsible for)