## Adoption Requirements
Requirement | Details
Key Objectives
Who will be involved in research and planning
Directly Impacted User Groups
Indirectly Impacted User Groups
Funding Sources
Who will be involved in implementation
Measurement
Reporting
Sign Off

## Capabilities and Processes
No. | Name | Description | Owner | Department/Function | Explanation of Impact | Impacted Users
Capability / Process 1 | Taking New Orders from Customers for Product X | The capability to document the custom requirements for Product X from a new customer, confirm production and shipping times with them, offer and (if required) provide finance options, gain financing approval (if required), get contract signed and place ne worder in production queue to be produced | VP Global Sales, Chris Hutchinson | Sales | New joined up sales, finance, manufacturing and distribution software system that enables orders placed by sales people to be automatically referred for finance and when approved to be added to the manufacturing queue and ultimately to the distribution worklist. The new software simplifies the custom ordering process for Product X and reduces time to delivery for the customer by up to three weeks | All Sales Staff
Capability / Process 2
Capability / Process 3
Capability / Process 4
Capability / Process 5
Capability / Process 6
Capability / Process 7
Capability / Process 8
Capability / Process 9
Capability / Process 10

## Impacted Groups
IG | Name | Description | Changes | Knowledge | Skills | Attitude
Group 1 | Head Office Reservations | Reservations Team at Head Office. Six team members. Good IT skills. Good language skills. Perform training and support duties as well as their own tasks | Full use of new RoomStacker reservations system | Basic concepts how the system works, plus specific tasks on the system described under "skills" | Search for an existing reservation Cancel an existing reservation Amend an existing reservation Provide refunds Search for available rooms Make a new reservation Take a deposit Create management reports | Probably good, as they expect the new system to help reduce their workload
Group 2 | Head Office Management | Senior and Middle Management at Head Office. Ten in total. Good English language skills. | Use of the new system for management reporting and decision making only | Basic concepts of how the system works, plus specific tasks on the system described under "skills" | Management reporting | Limited time available. Need to lay on multiple sessions for them to select from and communicate that this is a priority to ensure they turn up to the training session
Group 3 | Head Office IT | IT team of eight people at Head Office. Management and maintenance of the datacenter and software systems | Technical awareness of how to manage, maintain and support the RoomStacker reservations system | Full details on how the system works, and how it is installed, configured, managed and maintained | Ongoing management, maintenance and security | Fully on board, ready to go
Group 4 | Hotels Reception Teams | Reception Teams at each hotel. 27 hotels each with five to twelve people in the team. | Full use of new RoomStacker reservations system for all reception related tasks | Basic concepts how the system works, plus specific tasks on the system described under "skills" | Search for an existing reservation Check in process Allocate room Re-allocate room Check out process Amend an existing reseveration | Unknown, need to find out - might vary between locations
Group 5 | Hotels Management Teams | Management Teams at each hotel. 27 hotels each with minimum of four managers (one "manager plus three "deputies") in the team. | Full use of new RoomStacker reservations system for all reception related tasks and for management reporting | Basic concepts how the system works, plus specific tasks on the system described under "skills" | Search for an existing reservation Check in process Allocate room Re-allocate room Check out process Amend an existing reseveration Create management reports | Unknown, need to find out - might vary between locations
Group 6
Group 7
Group 8
Group 9
Group 10

## Practical Considerations
Consideration | Documentation | Ownership
Implementation Phases | Priority 1 = IT Team Priority 2 = Head Office (Reservation and HQ Management) Priority 3 = Hotels (Reception and Hotel Management) | CSM and SPL
User Availability | For continuity of service, provide the following: 2 x 1 day courses for IT team 2 x 1/2 day courses for Reservations team 3 x 1-2 hour courses for HQ Management 2 x half day courses for each region for all hotel staff (six half day courses in total) | CSM and SPL
External Dependencies | Check on installation and configuration of customer's new system, but proceed with training on our own demo system | CSM
Internal Dependencies | Ensure senior management (ie CEO and Head of Finance) make it a priority to communicate the importance of attendance and participation | SPL
Financing | Agreed and in place. Check on end user support for Reservations team | CSM
Deadlines and Timeframes | Must go live in four weeks | CSM and SPL
Milestones and KPIs | 1. Sign off on training and competence for IT team 2. Sign off on training and competence for Reservations team 3. Sign off on training and competence for HQ Management team 4. Sign off on training and competence for Region 1 Hotel Reception and Management teams 5. Sign off on training and competence for Region 2 Hotel Reception and Management teams 6. Sign off on training and competence for Region 3 Hotel Reception and Management teams | CSM and SPL
Internal and External Standards | N/A - need to validate?